## 5-3-23 by year
Potential Capital Improvement Projects for the Town of Irvington
5/3/23 version
Expected Expenditures by Year |  |  |  |  | Year of Expenditures
Project | Cost Range | Estimate Quality | Comment | Funding Source | FY 22-23 | FY 23-24 | FY 24-25 | FY 25-26 | FY 26-27 | FY 27-28
Sewer
Preliminary Engineering Report | $40K-$80K |  | FY22-FY23 | ARPA | Year of Expenditures FY 23-24: $40-$80K
Town Center Sewer | $2.3-$3.2 million | Ball Park | Awaiting outcome of Preliminary Engineering report | Debt by new taxes
Whole Town Sewer | $7.2-$9.8 | Ball Park | as above | Debt by new taxes
Commons Development
Playground upgrade | $25K |  | In process | ARPA | Year of Expenditures FY 22-23: $25K
Landscaping Plan | 25K |  | PC May Review | ARPA,Capital Reserves,Grants | Year of Expenditures FY 23-24: $25K
Tennis and Pickle Ball Court Rebuild | $150K | Quote | Priority 1 | Capital Reserves, Grants | Year of Expenditures FY 23-24: $150k
"Sprucing Up": landscaping, picnic tables, benches and shade | 75 | Ball Park | Priority 2, needs more definition | Capital Reserves, Grants | Year of Expenditures FY 23-24: $75K
Public Rest Rooms (Potentially in conjunction with Town Hall) | $75K | Ball Park | Await decision on Town Hall | Capital Reserves, Grants | Year of Expenditures FY 24-25: $75K
Drainage issues | $100K | Ball Park | Priority 2, needs more definition | Capital Reserves, Grants | Year of Expenditures FY 23-24: $50K; Year of Expenditures FY 24-25: $50K
Walkability
Cathie's Garden to Vineyard-800 ft | $75K | ball park | Priority 1 | Capital Reserves, Grants | Year of Expenditures FY 23-24: $75K
West Irvington- 2500 ft |  |  | Future Consideration
Steamboat rd to Old Mill Cove Rd-3300 ft |  |  | Future Consideration
TriWay Trail |  |  | Future Consideration
Town Office | $400K | Ball Park | Priority 1, The Town currently rents and has contract through 2025. Town needs alternative in place before end of 2025! | Mortgage and Capital Reserves |  | $100K | $28K | $28K | $28K | $28K
Public Waterfront | No location or cost identified |  | Support for ROR on Gaskins
Traffic Calming | No Scope or Estimates | N/A | Funding might be all State
Totals |  |  |  |  | $25k | $555K | $153K | $28K | $28K | $28K